## Sheet1
PROGRAMMING 2 PROJECT PROGRESS CHART
PLANNED SCHEDULES | WEEK12 | WEEK13 | WEEK14 | WEEK15 | WEEK16 | WEEK17 | WEEK18 | WEEK19 | WEEK20 | WEEK21
| Interim Project submitted: no master template, only sound visulaizer soley | Putting Particle sound visualizer into Vis-master music template. Requires to change and modify most of functions used but keep the concept. |  | Upgrading existing Particle sound visualizer to somewhat different version. Requires changes of features and functions compare to last submission. |  | Creating one more visualizer, as for now it will be perline noise visualizer. |  | modifying and upgrading new visualizers | Adding extensions on existing visualizers. | Wrapping up reports, progrss planner, debugging, final test with one of my friendwho is gonna be user.
ACTUAL PROGRESS REPORT AS IT PROCESSED | WEEK12 | WEEK13 | WEEK14 | WEEK15 | WEEK16 | WEEK17 | WEEK18 | WEEK19 | WEEK20 | WEEK21
| Interim project submitted, did not realize that there was a master template that we supposed to use. Started implementing as planning them. | READ.ME File gave some guidance for what needs to be done within the template itself. Researching and implementing to template as it says. | I had hard time to manage time and schdules, a lot of debuggings for putting my interim project file in to master template. | Sound visualizer upgraded as it got removed rotating function. color changes and size of circular motion changes as mouse moves on x - axis. A lot of debugging completed as it sometimes crashes with duplicated name or functions from existing template. |  | Creating new sound visualizer inspired by perlin noise effect. Putting each particles in perlin as amp/fft function so that it get size differences depends on how music I playing |  | Still on same task as last week. Also modifying existing visualizers at same time. | As we learned about GUI and user review from the lectures. I have tried to implement some functiones from gui. As well as wrapped about reports and all the writings as due dates are soon.
Planned Gannt
Partical vis to template
Upgrading 1
Create Perlin
modifying all
upgrade 2 : perlin
extension
report, paper works
Actual Gannt
Partical vis to template
Upgrading 1
Create Perlin
modifying all
upgrade 2 : perlin
extension
report, paper works
implement as READ ME